## Sheet1
|  | 2012-10-22 | 2012-10-29 | 2012-11-05 | 2012-11-12 | 2012-11-19 | 2012-11-26 | 2012-12-03
Design & Planning | Model | Initial Design Meeting | Maintenance |  | Expanded Scope Meeting | Maintenance | Maintenance
| UI | 2012-10-29: Initial Design Meeting; 2012-11-12: Design Finessing
Coding & Development | VirtualRepository | 2012-10-29: Initial Implemenation; 2012-11-05: Bugfixing
| RemoteRepository | 2012-11-12: Initial Implementation; 2012-11-19: Bugfixing
| LocalRepository | 2012-10-22: Initial Implemenation; 2012-10-29: Bugfixing; 2012-11-19: Remote compatibility check
| Task | 2012-10-22: Initial Implemenation; 2012-10-29: Bugfixing; 2012-11-19: Remote compatibility check
| Requirement | 2012-10-22: Initial Implemenation; 2012-10-29: Bugfixing; 2012-11-19: Remote compatibility check
| Fulfillment | 2012-10-29: Initial Implemenation; 2012-11-05: Bugfixing; 2012-11-19: Remote compatibility check
| RootActivity | 2012-10-29: Initial Implemenation; 2012-11-05: Bugfixing; 2012-11-19: Remote compatibility check
| TaskActivity | 2012-10-29: Initial Implemenation; 2012-11-05: Bugfixing; 2012-11-19: Remote compatibility check
| FulfillmentActivities | 2012-10-29: Initial Implemenation; 2012-11-05: Bugfixing; 2012-11-19: Remote compatibility check
| TaskListAdapter | 2012-10-29: Initial Implemenation; 2012-11-05: Bugfixing; 2012-11-19: Remote compatibility check
| RequirementListAdapter | 2012-10-29: Initial Implemenation; 2012-11-05: Bugfixing; 2012-11-19: Remote compatibility check
| FulfillmentListAdapter | 2012-10-29: Initial Implemenation; 2012-11-05: Bugfixing; 2012-11-19: Remote compatibility check
Artistic Design | RootActivity | 2012-10-22: Initial Layout; 2012-11-05: Rework Layout/Color; 2012-11-19: Aesthetic Touch-ups
| TaskActivity | 2012-10-22: Initial Layout; 2012-11-05: Rework Layout/Color; 2012-11-19: Aesthetic Touch-ups
| ImageCaptureActivity | 2012-10-29: Initial Layout; 2012-11-12: Rework Layout/Color; 2012-11-19: Aesthetic Touch-ups
| AudioCaptureActivity | 2012-10-29: Initial Layout; 2012-11-12: Rework Layout/Color; 2012-11-19: Aesthetic Touch-ups
| TextCaptureActivity | 2012-10-29: Initial Layout; 2012-11-12: Rework Layout/Color; 2012-11-19: Aesthetic Touch-ups